# Gran Boulva — Launch Plan

This launch plan is built for:

- a social platform

- a creator-driven ecosystem

- a culturally specific audience

- a retention-heavy product

- a low-budget but high-viral-potential startup

The goal is NOT:

“launch and hope people come”

The goal is:

# engineer momentum

You are not launching:

- an app

You are launching:

# a social environment

That changes the strategy completely.

# CORE LAUNCH STRATEGY

Gran Boulva succeeds if:

- users immediately see activity

- debates feel alive

- creators feel important

- sharing becomes natural

- users return daily

That means:

## empty platform = death

So the launch strategy is about:

# manufacturing initial energy

# PHASE 0 — PRE-LAUNCH FOUNDATION

## Timeline: 30–45 Days Before Launch

# Objective:

Build curiosity + recruit seed users.

# 1. Recruit 25–50 Seed Creators

VERY IMPORTANT.

Find:

- TikTok Haitians

- Facebook personalities

- sports debaters

- music fan pages

- political commentators

- funny personalities

- diaspora influencers

These people are NOT celebrities.

You want:

highly opinionated active people

Goal:
Make them feel like:

# founding voices

# 2. Build Closed WhatsApp + Discord Groups

Purpose:

- feedback

- hype

- creator onboarding

- content coordination

These become:

# your launch army

# 3. Create 100+ Matchups BEFORE Launch

The app must NEVER feel empty.

Prepare:

- music matchups

- politics

- sports

- diaspora issues

- funny topics

- controversial topics

Also:

- preload arguments

- preload predictions

- preload creator accounts

Users must feel:

people are already here

# 4. Create Social Media Content Engine

Platforms:

- TikTok

- Instagram Reels

- Facebook

- X/Twitter

DO NOT market the app directly at first.

Instead:
post:

- debates

- rankings

- predictions

- controversial questions

- creator battles

Example:

T-Vice vs Klass — kiyès ki toujou pi enfliyan?

This builds:

# emotional investment before launch

# 5. Create Waitlist System

Simple landing page:

- email

- phone number

- early access

Offer:

Founding Member Badge

This creates:

- exclusivity

- identity

- urgency

# PHASE 1 — SOFT LAUNCH

## Timeline: Week 1

# Objective:

Test retention + create activity density.

DO NOT publicly launch immediately.

# 1. Invite-Only Access

Start with:

- 200–500 users

Why?

Social apps fail when:

- too many empty spaces exist

- engagement density is weak

You need:

# concentrated activity

# 2. Daily Matchup Drops

Every day:
release:

- 5–10 strong debates

Focus on:

- highly emotional topics

- culturally relevant discussions

- music

- politics

- sports

# 3. Force Creator Activity

For first 2 weeks:
personally coordinate creators.

Ask them to:

- post arguments

- reply

- debate

- support

- challenge each other

You are:

# staging the party

# 4. Push Notifications

Critical.

Examples:

🔥 120 moun ap debat kestyon sa
👑 Ou monte #5 nan kategori mizik
⚡ Nouvo matchup viral disponib

Notifications create:

# return behavior

# 5. Watch These Metrics OBSESSIVELY

# Most Important:

- Day 1 retention

- Day 7 retention

- daily active users

- votes per user

- arguments per user

- sessions per day

NOT downloads.

Downloads mean nothing.

# PHASE 2 — VIRAL LAUNCH

## Timeline: Weeks 2–6

# Objective:

Explode organic sharing.

# 1. Shareable Matchup Cards

CRITICAL feature.

Users should share:

- votes

- rankings

- predictions

- creator battles

to:

- WhatsApp

- Instagram

- TikTok

- Facebook

These become:

# free distribution

# 2. Creator Rivalries

Encourage:

Top debater vs top debater

People LOVE social competition.

# 3. Weekly Rankings

Examples:

- Top Debater

- Most Influential Voice

- Fastest Growing Creator

- Prediction Champion

This creates:

# identity loops

# 4. Launch Referral Program

Example:

Invite 5 friends → unlock exclusive badge + boost

Do NOT offer generic cash rewards initially.

Status > money early on.

# 5. TikTok Strategy

This is HUGE.

Post:

- matchup animations

- creator arguments

- funny debate reactions

- prediction results

FAST editing.
High emotion.
Captions mandatory.

# PHASE 3 — COMMUNITY EXPANSION

## Timeline: Months 2–4

# Objective:

Turn users into creators.

# 1. Push Creator Identity HARD

Users must feel:

I can become known here

Add:

- creator badges

- rankings

- profile frames

- influence levels

# 2. Launch Coin Economy

Start:

- creator support

- boosts

- cosmetics

Do NOT over-monetize early.

# 3. Introduce Events

Examples:

- music tournaments

- prediction competitions

- election debates

- sports finals

Live moments create:

# explosive engagement

# 4. Expand AI Scout

Continuously generate:

- trending Haitian topics

- viral matchups

- predictions

This keeps content fresh daily.

# PHASE 4 — SCALE

## Timeline: Months 4–12

# Objective:

Become culturally unavoidable.

# 1. Partner With Influencers

Target:

- Haitian TikTokers

- music creators

- comedians

- diaspora creators

Not traditional celebrities first.

# 2. Launch Creator Monetization

Introduce:

- creator support payouts

- subscriptions

- premium communities

# 3. Build “Gran Boulva Personalities”

This is where platforms become powerful.

Users should recognize:

- top debaters

- top predictors

- controversial voices

- funny creators

# MARKETING THAT ACTUALLY WORKS

# What WILL work:

✅ TikTok clips
✅ WhatsApp sharing
✅ Facebook debate screenshots
✅ creator rivalries
✅ controversial topics
✅ live event matchups
✅ humor
✅ rankings
✅ social status systems

# What WON’T work:

❌ expensive ads early
❌ polished corporate campaigns
❌ influencer-only strategy
❌ generic startup branding
❌ press releases
❌ broad non-Haitian targeting early

# BIGGEST RISK

Your biggest risk is NOT:

- competition

It is:

# low retention

If users do not:

- return daily

- feel recognized

- see active discussions

the platform dies.

# SUCCESS METRICS

# Early Stage

You want:

- 30%+ Day 1 retention

- 15%+ Day 7 retention

- 5+ sessions per week

- strong sharing behavior

# Strong Signs

- creator rivalries emerge naturally

- people argue emotionally

- users share debates externally

- notifications drive returns

- users recognize personalities

That means:

# culture is forming

# MOST IMPORTANT PRINCIPLE

Do NOT think:

“How do we get users?”

Think:

# “How do we create a digital Haitian social arena people emotionally NEED to return to?”